## To Do List Check Box
TO DO LIST
# | Date | Activities / Tasks / Items | Priority | Completed | Status inputs | Priority | Weightage
1 | 31/10/2025 | Create GitHub repository | High | TRUE | Completed | High | 5
2 | 2025-01-10 | setup branches (main, dev, frontend, backend) | High | TRUE | In Progress | Medium | 3
3 | 2015-09-08 | Initialize React.js project structure (frontend folder) | Medium | FALSE | Not Started | Low | 1
4 | 2015-09-08 | Design landing page wireframe in Figma | Medium | TRUE
5 | v | mplement landing page in React | High | FALSE | Total Activities | 22
6 | v | Review and merge landing page branch into dev | Medium | FALSE | Completed Score | 13
7 | v | Setup Node.js + Express.js backend project (backend folder) | High | FALSE | Total Score | 92
8 | v | Create Technician Registration API with JWT | High | FALSE | % Completed | 14.13%
9 | v | Test registration API using Postman | Medium | FALSE
10 |  | Push and merge backend API to dev | Medium | FALSE
11 |  | Create Mongoose models for Users & Technicians | Medium | FALSE
12 |  | Implement database connection with MongoDB Atlas | High | FALSE
13 |  | ntegrate Stripe Payment Gateway (test key) | High | FALSE
14 |  | Connect frontend booking form to backend API | High | FALSE
15 |  | Conduct internal testing of all modules | High | FALSE
16 |  | Fix UI bugs and backend errors | Medium | FALSE
17 |  | Deploy backend on Render/Vercel | High | FALSE
18 |  | Deploy frontend on Netlify | High | FALSE
19 |  | Integration testing between both deployments | Medium | FALSE
20 |  | Prepare final documentation | High | FALSE
21 |  | Prepare final presentation slides | Medium | FALSE
22 |  | Merge dev → main and tag release | High | FALSE
23 |  |  |  | FALSE
24 |  |  |  | FALSE
25 |  |  |  | FALSE
14.1%